## Instructions
Taken from | https://www.teamgantt.com/free-gantt-chart-excel-template
Timeline | check dates for weeks 2021
add in Easter if you want to plan work here
Activities | check all the dummy events already in the spreadsheet and change as required
add in all YOUR activities
identify with a number in a cell when this is activity planned to take place and enter how many hours it will take
make sure the hours add up for that tasks
%complete | before submitting this in week 6 enter what you consider is the %complete for all activities
TOTAL | add up all you planned hours (16 credits = 160 hrs +/- 10%)

## Sample
C++ Gantt Chart
C++ Game Project | HOURS | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Planning & Preparation | 46
Attend Support Lectures | 36 | WEEK 1 Th: 3; WEEK 2 Th: 3; WEEK 3 Th: 3; WEEK 4 Th: 3; WEEK 5 Th: 3; WEEK 6 Th: 3; WEEK 7 Th: 3; WEEK 8 Th: 3; WEEK 9 Th: 3; WEEK 10 Th: 3; WEEK 11 Th: 3; WEEK 12 Th: 3
Topic Choice, initial research | 10 | WEEK 1 M: 2; WEEK 1 T: 2; WEEK 1 W: 2; WEEK 1 Th: 2; WEEK 1 F: 2
Technical Content | 46
Game Design Document | 10 | WEEK 6 W: 2; WEEK 7 W: 2; WEEK 8 W: 2; WEEK 9 W: 2; WEEK 10 W: 2
Technical Design Document | 10 | WEEK 11 M: 5; WEEK 11 T: 5
Test Plan | 10 | WEEK 11 W: 5; WEEK 12 W: 5
Git Commit Log | 12 | bar: WEEK 1 F; WEEK 2 W to WEEK 2 F; WEEK 3 F; WEEK 4 F; WEEK 5 F; WEEK 6 F; WEEK 7 F to WEEK 8 W; WEEK 8 F; WEEK 9 F; WEEK 10 W; WEEK 10 F; WEEK 11 F; WEEK 12 F
Schedule | 4 | bar: WEEK 2 W to WEEK 2 Th; WEEK 6 M; WEEK 8 M to WEEK 8 W; WEEK 10 M; WEEK 10 W; WEEK 12 M
C++ Project Completion | 81
Art Assets Creation in Aseprite | 18 | WEEK 2 M: 2; WEEK 2 W: 2; WEEK 2 F: 2; WEEK 3 M: 2; WEEK 3 W: 2; WEEK 3 F: 2; WEEK 8 M: 2; WEEK 8 W: 2; WEEK 8 F: 2
Coding in C++ | 54 | WEEK 1 M: 1; WEEK 1 W: 1; WEEK 1 F: 1; WEEK 2 Th: 3; WEEK 3 T: 3; WEEK 3 Th: 3; WEEK 4 T: 3; WEEK 4 Th: 3; WEEK 5 T: 3; WEEK 5 Th: 3; WEEK 6 T: 3; WEEK 6 Th: 3; WEEK 7 T: 3; WEEK 7 Th: 3; WEEK 8 T: 3; WEEK 8 Th: 3; WEEK 9 T: 3; WEEK 9 Th: 3; WEEK 10 T: 3; WEEK 10 Th: 3
Game Testing | 9 | bar: WEEK 2 W to WEEK 2 F; WEEK 3 F to WEEK 4 F; WEEK 5 F to WEEK 6 F; WEEK 7 F; WEEK 8 F; WEEK 9 F; WEEK 10 W; WEEK 10 F
TOTAL (160) | 173